## FRS Document
Requirement ID | Module | Sub Module | Requirement Description | Validation / Business Rules | Priority | Status
FR-01 | User Account | Registration | User should be able to register using name, email, and password | Validate email format and password complexity | P0 | Approved
FR-02 | User Account | Login | Registered users should be able to login securely | Allow login only with valid credentials | P0 | Approved
FR-03 | User Account | Logout | User should be able to logout and terminate session | Session should end across devices | P0 | Approved
FR-04 | User Account | Forgot Password | User should reset password using registered email | Reset link/token must be sent to email | P1 | Approved
FR-05 | Shopping | Product Search | User should search products using keywords | Display relevant results from title & description | P1
FR-06 | Shopping | Cart & Checkout | User should add products to cart and place order | Correct price calculation and checkout flow | P0
FR-07 | Shopping | Order History | User should view current and past orders | Orders should display correct status | P0
FR-08 | Shopping | Downloads | User should access purchased digital downloads | Allow access only after successful purchase | P2
FR-09 | Profile | Account Information | User should update personal details | Validate mandatory fields | P1 | Approved
FR-10 | Profile | Change Password | User should change password from profile | Old password validation required | P1
FR-11 | Payments | Payment Methods | User should manage saved payment methods | Secure storage and access | P1
FR-12 | Account | Showcase | User should view showcased items | Display active showcase items only | P2
FR-13 | Account | Partner Up | User should view/join Partner Up program | Optional feature | P3
FR-14 | Extensions | Extension Management | Admin/user should manage extensions | Install, enable, disable extensions | P3

## Test Scenario
Project Name | Opencart(Frontend)
Client | Opencart
Reference Document | FRS
Created By | Kishore Kumar R
Creation Date | Jan 15, 2025
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_01 | FRS | Validate the working of Register Account Functionality | P0 | 14
TS_02 | FRS | Validate the working of Login functionality | P0 | 18
TS_03 | FRS | Validate the working of Logout functionality | P0 | 12
TS_04 | FRS | Validate the working of Forgot Password functionality | P1 | 12
TS_05 | FRS | Validate the working of search functionality | P1
TS_06 | FRS | Validate the Account functionality | P1 | 20
TS_07 | FRS | Validate the working of Account > Account Information | P1
TS_08 | FRS | Validate the working of Account > Change Password | P1
TS_09 | FRS | Validate the working of Account > Payment Methods | P1
TS_10 | FRS | Validate the working of Account > Showcase | P2
TS_11 | FRS | Validate the working of Account > Partner Up | P3
TS_12 | FRS | Validate the Purchases functionality | P0
TS_13 | FRS | Validate the working of Purchases > Your Orders | P0
TS_14 | FRS | Validate the working of Purchases > Your Downloads | P2
TS_15 | FRS | Validate the working of Purchases > Your Stores | P2
TS_16 | FRS | Validate the working of Purchases > Rate your Downloads | P2
TS_17 | FRS | Validate the Extensions functionality | P3
TS_18 | FRS | Validate the working of Manage Your Extensions | P3
TS_19 | FRS | Validate the working of Apply to become a seller | P3

## Register
Test Case ID | Test Scenario | TestCase Title | Pre-requisities | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC_RF_001 | TS_001 Register Functionality | Validate Registering an Account by providing only the mandatory fields | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser | 1.Click on Register button 2.Enter valid Username, First Name, Last Name, Email, Country, Password 3.Solve captcha 4.Click on Register | Valid mandatory details | 1.User should be logged in, Taken to Account Success page and proper details should be displayed on the page. 2.User should be taken to Account page and a confirm email should be sent to the registered email address. |  |  | P0
TC_RF_002 | TS_001 Register Functionality | Validate register page UI elements | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser | 1.Click on Register 2.Verify Username, First Name, Last Name, Email, Country, Password fields 3.Verify Register button and captcha | Not Applicable | All mandatory fields, captcha and Register button should be visible |  |  | P1
TC_RF_003 | TS_001 Register Functionality | Validate registration with empty mandatory fields | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser | 1.Click on Register 2.Leave all fields blank 3.Click on Register | Empty values | Proper validation messages should be displayed for required fields |  |  | P0
TC_RF_004 | TS_001 Register Functionality | Validate email field with invalid email format | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser | 1.Enter invalid email (abc@) 2.Fill remaining mandatory fields 3.Click on Register | Invalid email format | System should display email validation erro |  |  | P1
TC_RF_005 | TS_001 Register Functionality | Validate registration with already registered email | Existing registered email | 1.Enter already registered email 2.Fill remaining mandatory fields 3.Click on Register | Existing email | Error message should be displayed stating email already exists |  |  | P0
TC_RF_006 | TS_001 Register Functionality | Validate password field with minimum characters | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser | 1.Enter password with less than required characters 2.Fill other mandatory fields 3.Click on Register | Weak Password | Password validation error should be displayed |  |  | P1
TC_RF_007 | TS_001 Register Functionality | Validate country dropdown selection | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser | 1.Click on Country dropdown 2.Select any country | Country name | Selected country should be displayed correctly |  |  | P2
TC_RF_008 | TS_001 Register Functionality | Validate captcha without selection | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser | 1.Fill all mandatory fields 2.Do not solve captcha 3.Click Register | Valid inputs without captcha | Captcha validation message should be displayed |  |  | P2
TC_RF_009 | TS_001 Register Functionality | Validate captcha refresh functionality | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser | 1.Click on captcha refresh icon | Not Applicable | New captcha images should be displayed |  |  | P1
TC_RF_010 | TS_001 Register Functionality | Validate Register button functionality | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser | 1.Fill all valid mandatory details 2.Click on Register button | Valid data | Register button should submit the form successfully |  |  | P2
TC_RF_011 | TS_001 Register Functionality | Validate redirection after successful registration | Valid registration data | 1.Complete registration successfully | Valid data | User should be redirected to Account Success page |  |  | P0
TC_RF_012 | TS_001 Register Functionality | Validate confirmation email after registration | Valid email address | 1.Complete registration 2.Check registered email inbox | Valid email | Confirmation email should be received |  |  | P0
TC_RF_013 | TS_001 Register Functionality | Validate page navigation from Home to Register | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser | 1.Click on Register from homepage | Not Applicable | User should navigate to Register page |  |  | P0
TC_RF_014 | TS_001 Register Functionality | Validate browser compatibility for register page | Different browsers | 1.Open Register page in Chrome, Firefox, Edge | Not Applicable | Register page should load correctly in all browsers |  |  | P0

## Login
Test Case ID | Test Scenario | TestCase Title | Pre-requisities | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC_001 | TS_001 Login Functionality | Page loads successfully | Open the Application (https://www.opencart.com/index.php?route=cms/demo in any browser and User must be registered | 1. Open browser 2. Enter OpenCart login URL | Valid URL | Login page is displayed with Email, Password, Login button | Login page loaded successfully |  | P1
TC_002 | TS_002 Login Functionality | Login with valid credentials | User must be registered | 1. Enter valid email 2. Enter valid password 3. Click Login | Valid email & password | User should be logged in successfully | User logged in successfully |  | P0
TC_003 | TS_003 Login Functionality | Login with invalid password | User must be registered | 1. Enter valid email 2. Enter invalid password 3. Click Login | Invalid password | Error message should be displayed | Error message displayed |  | P0
TC_004 | TS_004 Login Functionality | Login with invalid email | User must be registered | 1. Enter invalid email 2. Enter valid password 3. Click Login | Invalid email | Error message should be displayed | Error message displayed |  | P0
TC_005 | TS_005 Login Functionality | Login with empty email field | User must be on login page | 1. Leave email blank 2. Enter password 3. Click Login | Password only | Validation message should be shown | Validation message shown |  | P1
TC_006 | TS_006 Login Functionality | Login with empty password field | User must be on login page | 1. Enter email 2. Leave password blank 3. Click Login | Email only | Validation message should be shown | Validation message shown |  | P1
TC_007 | TS_007 Login Functionality | Login with empty email and password | User must be on login page | 1. Leave email blank 2. Leave password blank 3. Click Login | No data | Error message should be shown | Error message shown |  | P0
TC_008 | TS_008 Login Functionality | Check Forgot Password link | User must be on login page | 1. Click Forgot your password link | N/A | User should navigate to forgot password page | Navigated successfully |  | P2
TC_009 | TS_009 Login Functionality | Password field masked | User must be on login page | 1. Type password in password field | Password text | Password should be masked | Password masked |  | P3
TC_010 | TS_010 Login Functionality | Check login button enabled | User must be on login page | 1. Enter email 2. Enter password | N/A | Login button should be clickable | Login button clickable |  | P3
TC_011 | TS_011 Login Functionality | Login using unregistered email | User must be on login page | 1. Enter unregistered email 2. Enter password 3. Click Login | Unregistered email | Error message should be shown | Error message shown |  | P0
TC_012 | TS_012 Login Functionality | Verify error message text | User must be on login page | 1. Enter invalid credentials 2. Click Login | Invalid credentials | Proper error message should be displayed | Correct error message displayed |  | P2
TC_013 | TS_013 Login Functionality | Check email field placeholder | User must be on login page | 1. Observe email field | N/A | Email placeholder text should be displayed | Placeholder visible |  | P3
TC_014 | TS_014 Login Functionality | Check password field placeholder | User must be on login page | 1. Observe password field | N/A | Password placeholder text should be displayed | Placeholder visible |  | P3
TC_015 | TS_015 Login Functionality | Session maintained after login | User logged in successfully | 1. Login 2. Refresh page | N/A | User should remain logged in | Session maintained |  | P1
TC_016 | TS_016 Login Functionality | Logout after successful login | User logged in successfully | 1. Click Logout | N/A | User should be logged out successfully | User logged out |  | P1
TC_017 | TS_017 Login Functionality | SQL injection in login fields | User must be on login page | 1. Enter SQL query in email/password | SQL input | Login should be prevented | Login prevented |  | P0
TC_018 | TS_018 Login Functionality | Check Create Account link | User must be on login page | 1. Click Create an OpenCart account link | N/A | User should navigate to registration page | Navigated successfully |  | P2

## Logout
Test Case ID | Test Scenario | TestCase Title | Pre-requisities | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC_001 | TS_001 Logout Functionality | Page loads successfully | User must be logged in | 1. Login to application 2. Observe Logout option | N/A | Logout option should be visible | Logout option visible |  | P1
TC_002 | TS_002 Logout Functionality | Logout with valid session | User must be logged in | 1. Click Logout button | N/A | User should be logged out successfully | User logged out successfully |  | P0
TC_003 | TS_003 Logout Functionality | Redirect after logout | User must be logged in | 1. Click Logout | N/A | User should be redirected to login/home page | Redirected to login page |  | P0
TC_004 | TS_004 Logout Functionality | Session invalidation after logout | User must be logged in | 1. Click Logout 2. Press browser back button | N/A | User should not access account page | Session invalidated |  | P0
TC_005 | TS_005 Logout Functionality | Access protected page after logout | User logged out | 1. Enter account URL directly | Account URL | User should be redirected to login page | Redirected to login page |  | P0
TC_006 | TS_006 Logout Functionality | Logout link availability | User must be logged in | 1. Verify Logout link in header/menu | N/A | Logout link should be available | Logout link available |  | P1
TC_007 | TS_007 Logout Functionality | Logout using browser refresh | User must be logged in | 1. Click Logout 2. Refresh page | N/A | User should remain logged out | User remains logged out |  | P1
TC_008 | TS_008 Logout Functionality | Multiple logout clicks | User must be logged in | 1. Click Logout multiple times | N/A | User should be logged out without error | Logout handled correctly |  | P1
TC_009 | TS_009 Logout Functionality | Logout from multiple tabs | User logged in on multiple tabs | 1. Logout from one tab 2. Switch tab | N/A | Session should be terminated in all tabs | Session terminated |  | P0
TC_010 | TS_010 Logout Functionality | Security check after logout | User must be logged out | 1. Try accessing dashboard via URL | Dashboard URL | Access should be denied | Access denied |  | P0
TC_011 | TS_011 Logout Functionality | UI message after logout | User must be logged in | 1. Click Logout | N/A | Logout success message should be displayed | Message displayed |  | P1
TC_012 | TS_012 Logout Functionality | Login again after logout | User must be logged out | 1. Enter valid credentials 2. Click Login | Valid credentials | User should login successfully | User logged in successfully |  | P0

## Forgot
Test Case ID | Test Scenario | TestCase Title | Pre-requisities | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC_001 | TS_001 Forgot Functionality | Forgot password page loads | User must be on login page | 1. Click Forgot your password link | N/A | Forgot password page should be displayed | Page displayed successfully |  | P1
TC_002 | TS_002 Forgot Functionality | Forgot password with registered email | User must be registered | 1. Enter registered email 2. Click Continue | Valid registered email | Password reset link should be sent | Reset link sent successfully |  | P0
TC_003 | TS_003 Forgot Functionality | Forgot password with unregistered email | User must be on forgot password page | 1. Enter unregistered email 2. Click Continue | Unregistered email | Error message should be displayed | Error message displayed |  | P0
TC_004 | TS_004 Forgot Functionality | Forgot password with invalid email format | User must be on forgot password page | 1. Enter invalid email 2. Click Continue | Invalid email | Error message should be displayed | Error message displayed |  | P0
TC_005 | TS_005 Forgot Functionality | Forgot password with empty email field | User must be on forgot password page | 1. Leave email field blank 2. Click Continue | No data | Validation message should be shown | Validation message shown |  | P0
TC_006 | TS_006 Forgot Functionality | Email field placeholder | User must be on forgot password page | 1. Observe email field | N/A | Email placeholder should be visible | Placeholder visible |  | P1
TC_007 | TS_007 Forgot Functionality | Continue button enabled | User must be on forgot password page | 1. Enter email | N/A | Continue button should be clickable | Button clickable |  | P1
TC_008 | TS_008 Forgot Functionality | Reset email content verification | User must request reset | 1. Open received email | N/A | Reset email should contain valid link | Valid reset link present |  | P0
TC_009 | TS_009 Forgot Functionality | Reset link navigation | User must receive reset email | 1. Click reset link | N/A | User should navigate to reset password page | Navigated successfully |  | P0
TC_010 | TS_010 Forgot Functionality | Reset password with valid data | User must be on reset page | 1. Enter new password 2. Confirm password 3. Submit | Valid password | User password should be updated | Password updated successfully |  | P0
TC_011 | TS_011 Forgot Functionality | Reset password with mismatched passwords | User must be on reset page | 1. Enter password 2. Enter different confirm password | Mismatch passwords | Error message should be displayed | Error message displayed |  | P0
TC_012 | TS_012 Forgot Functionality | Login after password reset | User password reset completed | 1. Login with new password | New password | User should login successfully | User logged in successfully |  | P0

## Account
Test Case ID | Test Scenario | TestCase Title | Pre-requisities | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC_01 | Account Info | Edit First Name | User logged in & on Edit Info page | 1. Clear First Name 2. Enter new name 3. Click Submit | First Name: "John" | Profile updated successfully message appears |  |  | P1
TC_02 | Account Info | Edit Last Name | User logged in & on Edit Info page | 1. Clear Last Name 2. Enter new name 3. Click Submit | Last Name: "Doe" | Profile updated successfully message appears |  |  | P1
TC_03 | Account Info | Update E-Mail | User logged in & on Edit Info page | 1. Enter new valid email 2. Click Submit | valid@email.com | Email updated; verification may be required |  |  | P0
TC_04 | Account Info | Field Validation - Empty First Name | User logged in & on Edit Info page | 1. Clear First Name 2. Click Submit | Empty field | Error message: "First Name must be between 1 and 32 characters!" |  |  | P0
TC_05 | Account Info | Field Validation - Empty Last Name | User logged in & on Edit Info page | 1. Clear Last Name 2. Click Submit | Empty field | Error message: "Last Name must be between 1 and 32 characters!" |  |  | P0
TC_06 | Account Info | Invalid Email Format | User logged in & on Edit Info page | 1. Enter email without '@' 2. Click Submit | "https://www.google.com/search?q=testemail.com" | Error message regarding invalid email format |  |  | P0
TC_07 | Account Info | Update Company Name | User logged in & on Edit Info page | 1. Enter company name 2. Click Submit | "Tech Corp" | Profile updated successfully |  |  | P2
TC_08 | Account Info | Update Tax ID | User logged in & on Edit Info page | 1. Enter Tax ID 2. Click Submit | "TX12345" | Profile updated successfully |  |  | P2
TC_09 | Account Info | Country Selection | User logged in & on Edit Info page | 1. Select country from dropdown 2. Click Submit | "United States" | Selection saved successfully |  |  | P1
TC_10 | Profile Pic | Upload Profile Picture | User logged in & on Profile page | 1. Click Browse 2. Select image 3. Click Submit | JPG/PNG file | Image uploaded and displayed in profile |  |  | P2
TC_11 | Profile Pic | Clear Profile Picture | User has profile picture | 1. Click Clear 2. Click Submit | N/A | Image removed; default placeholder shown |  |  | P2
TC_12 | Preferences | Toggle Extension Updates | User logged in & on Profile page | 1. Select 'Yes' for notifications 2. Click Submit | Radio button: Yes | Preference saved successfully |  |  | P2
TC_13 | Navigation | Side Menu - Change Password | User logged in | 1. Click 'Change password' in sidebar | N/A | Navigates to Change Password page |  |  | P1
TC_14 | Navigation | Side Menu - Payment Methods | User logged in | 1. Click 'Payment Methods' in sidebar | N/A | Navigates to Payment Methods page |  |  | P2
TC_15 | Navigation | Side Menu - Purchases | User logged in | 1. Click 'Purchases' accordion | N/A | Purchases section expands to show options |  |  | P1
TC_16 | Security | Unauthorized Access | User not logged in | 1. Try to access /account URL directly | URL path | Redirected to Login page |  |  | P0
TC_17 | Session | Logout Functionality | User logged in | 1. Click Logout button in header | N/A | User logged out; session destroyed |  |  | P0
TC_18 | Account Info | Read-only Username | User logged in & on Edit Info page | 1. Attempt to type in Username field | N/A | Field should be disabled or non-editable |  |  | P2
TC_19 | UI/UX | Form Reset/Cancel | User logged in & on Edit Info page | 1. Change fields 2. Click Cancel | N/A | Changes discarded; returns to account dash |  |  | P1
TC_20 | Account Info | Verify Character Limits | User logged in & on Edit Info page | 1. Enter 33+ characters in First Name | Long string | Should show error or truncate at limit |  |  | P2

## RTM_OpenCart
Requirement ID | Requirement Description | Test Case ID | Module | Status
FRS_REG_01 | User should register with valid data | TC_REG_01 | Register | Covered
FRS_LOG_02 | User should login with valid credentials | TC_LOG_02 | Login | Covered
FRS_LOG_03 | User should be able to logout and terminate session | TC_ACC_03 | Logout | Covered
FRS_FOR_04 | User should reset password using registered email | TC_FOR_04 | Forgot | Covered
FRS_ACC_09 | User should update personal details | TC_ACC_09 | Account | Covered

## Sample_Defect_Report
Defect ID | Summary | Module | Steps | Expected | Actual | Severity | Status
BUG_01 | Login allows invalid email | Login | Steps... | Error msg | Login success | High | Open

## Test_Execution_Report
Test Case ID | Module | Result | Executed By | Date
TC_REG_01 | Register | Pass | Kishore Kumar | 2026-01-20
TC_LOG_02 | Login | Fail | Kishore Kumar | 2026-01-21
TC_Log_03 | Logout | Pass | Kishore Kumar | 2026-01-22
TC_FOR_04 | Forgot | Pass | Kishore Kumar | 2026-01-23
TC_ACC_05 | Account | Pass | Kishore Kumar | 2026-01-24